# Overall plan for roll out

# Project Rollout Plan (Feb 26 – Mar 31, 2026)

Goal: Complete all projects (except McCarthy Phase 2 expansion) by March 31, 2026, while maintaining revenue, compliance, and operational stability during tax season.

# Overview of Projects

| Project | Purpose | Key Considerations | Completion Date |
| --- | --- | --- | --- |
| 1B → 3B Upgrade System (IDIQ Process) | Allow clients to start with 1 Bureau (1B) and upgrade to 3 Bureau (3B) | Revenue-impacting; requires rebuild protocol; consultant training critical | March 6, 2026 |
| McCarthy Phase 1 | Integrate litigation process for clients NOT currently in services | Must prevent disputes once accepted; app training required; supervised launch | March 16, 2026 (Full Handoff) |
| Playbook Stabilization (V1) | Centralized operational documentation | Focus on Phase 1 tabs only; calendar + knowledge base prioritized | March 31, 2026 |
| McCarthy Phase 2 | Expand litigation offering to all active clients | Requires dispute suppression system before launch | April 1–14, 2026 (Q2 Weeks 1–2) |

# Phase 1 – 1B → 3B Upgrade System (IDIQ Process)

Timeline: Feb 26 – March 6
 Priority: Highest (Revenue & Client Experience)

### Key Deliverables & Dates

| Deliverable | Completion Date |
| --- | --- |
| Finalize consultation scripts for 1B clients | Feb 28, 2026 |
| Build upgrade workflow (post-sale) | Mar 2, 2026 |
| Define dispute rebuild protocol after upgrade | Mar 2, 2026 |
| Create manager audit checklist | Mar 3, 2026 |
| Train consultants on scripts + workflow | Mar 4–5, 2026 |
| Update Playbook with full 1B → 3B flow | Mar 6, 2026 |
| System fully live & tested | Mar 6, 2026 |

### Outcome by March 6:

- Fully operational 1B → 3B process

- Consultants trained and confident

- Live cases tested

- Revenue and dispute workflow stabilized

# Phase 2 – McCarthy Phase 1 (Clients NOT in Services)

Timeline: March 3 – March 16
 Priority: Legal-sensitive, controlled rollout

⚠️ Phase 1 ONLY applies to:

- Clients not yet started

- Clients about to end services

- NOT active dispute clients

### Execution Timeline

| Date | Milestone | Owner |
| --- | --- | --- |
| Mar 3–4 | Joe trains Kim on McCarthy app | Joe |
| Mar 4 | Phase 1 process documented | Leadership |
| Mar 5 | Team review + walkthrough | Joe / Astrid |
| Mar 6 | Supervised team launch begins | Team w/ Joe & Astrid |
| Mar 9–13 | Team handles calls (supervised) | Team |
| Mar 16 | Full team handoff to Kim | Kim |

### Required System Controls

- Accounts accepted for litigation must NOT be disputed

- Clear “Accepted – Do Not Dispute” tagging system

- Manager-level oversight during supervised week

### Outcome by March 16:

- Internal system stable

- Team operating process

- No disputes touching litigation accounts

- No reliance on Google Sheets

# Phase 3 – Playbook Stabilization (V1)

Timeline: March 9 – March 31
 Priority: Operational clarity & scalability

### Week of March 9–13 (While Kim is Away)

Focus: Mariana + Astrid

| Focus Area | Completion Target |
| --- | --- |
| Outline Phase 1 Tabs | Mar 13 |
| Calendar Features Structure | Mar 13 |
| Knowledge Base Framework | Mar 13 |

### Remaining March Deliverables

| Section | Completion Date |
| --- | --- |
| 1B Blueprint Flow Documentation | Mar 15 |
| 3B Upgrade Rebuild Process | Mar 18 |
| McCarthy Phase 1 Process | Mar 21 |
| Dispute Suppression Protocol (for Phase 2 readiness) | Mar 24 |
| Playbook V1 (Skeleton Complete) | Mar 31, 2026 |

### Outcome by March 31:

- Playbook V1 completed

- Managers know where to find workflows

- Reduced tribal knowledge

- Team accountability improves

# McCarthy Phase 2 (Q2 Weeks 1–2)

April 1–14, 2026

⚠️ This phase expands litigation offering to ACTIVE clients.

### Must Be Built Before Launch:

- Litigation Tag System

- “Accepted – Do Not Dispute” Status

- Manager Override Controls

- Dispute Suppression Checklist

- Consultant Training for Litigation Conversations

# Critical Risk Management

| Risk | Mitigation |
| --- | --- |
| Disputes on accounts under litigation | Mandatory tagging + manager approval |
| Refunds / dissatisfaction (1B → 3B) | Clear scripts + transparent upgrade explanation |
| Team fatigue during tax season | Staggered training + supervised rollout |
| Operational confusion | Playbook V1 + audit checklist |
| Legal exposure | Controlled rollout before Phase 2 expansion |

# Clear Executive Summary of Hard Deadlines

- ✅ March 6 – IDIQ (1B → 3B) fully live

- ✅ March 16 – McCarthy Phase 1 fully handed to Kim

- ✅ March 31 – Playbook V1 complete

- 🔜 April 1–14 – McCarthy Phase 2 launch window

# Deadlines for each Project

# 📊 MASTER DEADLINE CHART

| Deadline | Project | What Must Be Completed | Owner(s) | Status Definition |
| --- | --- | --- | --- | --- |
| March 4 | McCarthy Phase 1 | Full process documented (workflow, offers, follow-ups, escalation) | Joe / Kim / Astrid | Manager can execute without asking Joe questions |
| March 5 | McCarthy Phase 1 | Team review + walkthrough completed | Joe / Astrid | Team ready for supervised execution |
| March 6 | IDIQ (1B → 3B) | Fully operational system (script, upgrade flow, rebuild process, training complete) | Astrid / Consultants | Clients can enter, upgrade, and rebuild disputes without confusion |
| March 6 | McCarthy Phase 1 | Supervised team launch begins | Joe / Astrid | Team making calls under supervision |
| March 13 | Playbook Phase 1 Structure | Tabs outlined, calendar + knowledge base structured | Mariana / Astrid | Core framework usable internally |
| March 16 | McCarthy Phase 1 | Full team takeover | Kim/Account Managers | Process runs without daily leadership oversight |
| March 31 | Playbook V1 | Phase 1 documentation finalized | Mariana / Astrid | No tribal knowledge required |
| April 1–14 | McCarthy Phase 2 | Active client expansion + dispute suppression system | Leadership Team | Safe to expand to active clients |

# 📊 IDIQ (1B → 3B) COMPLETION CHART

Deadline: March 6

| Component | Required by 3/6? | Owner | Completion Standard |
| --- | --- | --- | --- |
| Consultation Script | ✅ | Astrid | Final version approved |
| Upgrade Workflow | ✅ | Leadership | Clear post-sale steps defined |
| Dispute Rebuild Protocol | ✅ | Operations | Written & tested |
| IDIQ Login/Security Flow | ✅ | Operations | No access confusion |
| Manager Audit Checklist | ✅ | Astrid | QA system created |
| Consultant Training | ✅ | Astrid | Team trained & tested |
| Live Case Testing | ✅ | Team | Running smoothly |

# 📊 McCarthy Phase 1 TRANSITION CHART

(Clients NOT in services)

| Date | Execution Stage | Who Is Operating | Who Is Supervising |
| --- | --- | --- | --- |
| March 4 | Process Complete | Managers | Joe / Astrid review |
| March 5 | Team Review | Full Team | Joe / Astrid |
| March 6 | Supervised Launch | Team | Joe / Astrid |
| March 9–13 | Controlled Execution | Team | Joe / Astrid |
| March 16 | Full Handoff | Team | Kim (Full Ownership) |

# 📊 Week of March 9–13 FOCUS CHART

| Area | Owner | Required Output by March 13 |
| --- | --- | --- |
| Playbook Phase 1 Tab Outline | Mariana / Astrid | Structure built |
| Calendar Features | Mariana / Astrid | Documented framework |
| Knowledge Base | Mariana / Astrid | Organized system created |
| IDIQ Process in Playbook | Mariana / Astrid | Written & structured |
| McCarthy Phase 1 in Playbook | Mariana / Astrid | Written & structured |

# 📊 McCarthy Phase 2 (Q2) PREPARATION CHART

April 1–14

| Requirement | Must Be Built Before Launch? | Risk Level |
| --- | --- | --- |
| Litigation Tag System | ✅ | High |
| “Accepted – Do Not Dispute” Status | ✅ | High |
| Manager Override Control | ✅ | High |
| Dispute Suppression Checklist | ✅ | High |
| Consultant Litigation Training | ✅ | Medium |

# To-do while I am off

# 📅 Coverage Window: Feb 27 – March 4

Owner out: Astrid
 Return date: March 4

Primary focus while you're out:

- Keep 1B → 3B deadline on track (March 6 go-live)

- Complete McCarthy Phase 1 documentation by March 4

- Avoid operational confusion during tax season

# 🔹 JOE – Responsibilities While Astrid Is Out

### 🔥 Highest Priority: McCarthy Phase 1 System

| Task | Deadline | Definition of Done |
| --- | --- | --- |
| Train Kim on McCarthy App (full functionality) | March 3 | Kim can operate without Joe |
| Clarify litigation acceptance flow | March 3 | Clear decision tree documented |
| Finalize Phase 1 eligibility criteria (non-active clients only) | March 3 | Written and approved |
| Ensure Phase 1 process is fully documented | March 4 | Manager-ready document |

### 🔥 Support 1B → 3B Project

| Task | Deadline | Definition of Done |
| --- | --- | --- |
| Review 1B consultation script | March 2 | Approved version |
| Approve upgrade pricing positioning | March 2 | Locked for launch |
| Confirm dispute rebuild authority process | March 3 | Managers know who approves |

# 🔹 KIM – Responsibilities While Astrid Is Out

### 🎯 McCarthy Phase 1 Process Owner

| Task | Deadline | Definition of Done |
| --- | --- | --- |
| Learn McCarthy App from Joe | March 3 | Can execute test case |
| Confirm no disputes rule for litigation accounts (see document 4 in this sheet) | March 3 | Written rule: “Accepted = Do Not Dispute” |
| Document step-by-step workflow | March 4 | Written SOP draft |
| Define intake tracking method | March 4 | No more Google Sheet reliance |
| Identify dispute suppression triggers | March 4 | List of accounts that must not be touched |
| Prepare team walkthrough outline | March 4 | Ready for March 5 review |

# 🔹 MARIANA – Responsibilities While Astrid Is Out

### 📘 Playbook Foundation Work (Independent Build Work)

| Task | Deadline | Definition of Done |
| --- | --- | --- |
| Outline Phase 1 Playbook Tabs | March 4 | Structural layout complete |
| Create Calendar Framework | March 4 | Defined structure for task tracking |
| Begin Knowledge Base Categories | March 4 | Organized sections created |
| Create placeholder for 1B → 3B Flow | March 4 | Framework ready for insertion |

⚠️ Mariana should NOT build detailed process without final approval — focus on structure only.

# 📌 What Must Be Ready When You Return (March 4)

By the time you are back:

### 1B → 3B

- Script approved

- Upgrade positioning approved

- Dispute rebuild authority defined

### McCarthy Phase 1

- Kim trained

- Workflow drafted

- Litigation accounts clearly marked “Do Not Dispute”

- Phase 1 limited to non-active clients confirmed

### Playbook

- Tabs structured

- Calendar skeleton built

- Knowledge base organized

# 📅 Immediate Actions Upon Your Return (March 4–6)

When you return, your focus becomes:

- Finalize McCarthy documentation (March 4)

- Conduct Team Review (March 5)

- Launch supervised McCarthy Phase 1 (March 6)

- Train consultants fully on 1B → 3B (if not already complete)

- Stress test dispute rebuild workflow

# 🚨 Critical Control Reminder (Non-Negotiable)

Before Phase 1 Launch:

- Any account accepted for litigation must be:

  - Tagged clearly

  - Removed from dispute cycle

  - Manager approved before any change

This must be built BEFORE March 6.

# Decision Tree for Kim

# 🧭 Step-by-Step Decision Tree

## STEP 1: Client Eligibility Check

Question 1:
 Is the client currently in active credit repair services with us?

- ✅ NO → Proceed to Step 2

- ❌ YES → STOP (Phase 1 does NOT apply)

## STEP 2: Report Review

McCarthy reviews report and identifies potential FCRA violations.

Question 2:
 Did McCarthy identify viable litigation accounts?

- ❌ NO → No offer made → Continue normal workflow

- ✅ YES → Proceed to Step 3

## STEP 3: Internal Validation

Before presenting to client:

- Confirm account is not actively being disputed

- Confirm no duplicate submission

- Confirm documentation is complete

If all verified → Proceed to Step 4

## STEP 4: Offer Presented to Client

Client is contacted and litigation opportunity is explained.

Question 3:
 Does client accept litigation offer?

- ❌ NO →

  - Mark as “Declined Litigation”

  - Continue normal workflow

  - No tagging required

- ✅ YES → Proceed to Step 5

## STEP 5: Litigation Acceptance Tag (CRITICAL CONTROL POINT)

Immediately upon acceptance:

- Apply system tag: “Accepted – Do Not Dispute”

- Remove account from dispute queue

- Lock account from automation

- Notify manager

This step must happen SAME DAY as acceptance.

## STEP 6: Confirmation to McCarthy

- Submit accepted case through official app

- Confirm receipt

- Log submission date

- Save documentation in client file

## STEP 7: Ongoing Protection

Once tagged:

- Account cannot be disputed

- No letters generated

- No system automation touching account

- Manager approval required to change status

# 🔐 Control Rules (Non-Negotiable)

- If Accepted → It is frozen from disputes.

- No manual override without manager approval.

- Tag must be visible to all team members.

- Audit review weekly during Phase 1.

# 📌 Definition of “Clear Decision Tree Documented”

This means:

- Written in SOP format (like above)

- Stored in Playbook

- Includes:

  - Eligibility rules

  - Acceptance tagging steps

  - Dispute suppression instructions

  - Escalation procedure

- Manager can execute without asking Joe

- Team can follow without guessing

# For Mariana

# PHASE 1 – PLAYBOOK FOUNDATION (Due March 4)

This is not about filling in content yet.
 This is about building the architecture so everything else plugs in cleanly.

Think: infrastructure before decoration.

# 1️⃣ Outline Phase 1 Playbook Tabs

Outcome: Structural layout complete

### Objective

Create a master tab structure that separates departments, processes, and escalation paths in a way that reduces cross-department confusion.

### How To Build It (Smart Structure)

Use this format inside the Playbook:

## 🔹 MASTER INDEX TAB (First Tab)

This is the command center.
 It should include:

- Department breakdown

- Quick links to each section

- Escalation flow reference

- Last updated date

- Version number

## 🔹 DEPARTMENT TABS

Create separate high-level tabs for:

- Consultants

- Account Managers

- Customer Support

- Leadership / Admin

- Automation / Zaps

- Compliance

- Metrics & KPIs

Each department tab should follow the SAME structure:

- Daily Responsibilities

- Filters Ownership

- Escalation Rules

- Scripts

- Training Links

- Common Errors

- Related Automations

Consistency is key. If every tab looks the same, no one has to “figure it out.”

## 🔹 ESCALATION MAP TAB

Visual decision tree:

- Who handles what first?

- When does it move up?

- When does it become urgent?

This prevents:

- Slack chaos

- Duplicate effort

- “I thought they were handling it”

# 2️⃣ Create Calendar Framework

Outcome: Defined structure for task tracking

This is not a calendar with dates yet.
 This is a repeatable system.

### Goal

Build a framework that answers:

- What repeats daily?

- What repeats weekly?

- What triggers manually?

- What is event-based?

## 🔹 Build 4 Sections

### 1. Daily Recurring

Examples:

- Timed Call filter checks

- Round Robin audits

- Payment filter clearing

- Logins not ready check

### 2. Weekly Recurring

Examples:

- 5-day follow-ups

- 15-day filter audits

- Duplicate audit

- Refund audit

- Metrics review

### 3. Monthly Recurring

Examples:

- Script updates

- KPI review

- Automation audit

- Training refreshers

### 4. Event-Based Tasks

Examples:

- Client moves to AP

- Client upgrades to 3B

- Refund requested

- Zap failure

### Make It Smart

Each calendar item should include:

- Owner

- Backup owner

- Trigger

- Where it's tracked (Filter / Zap / Manual)

- KPI tied to it

This prevents “floating responsibilities.”

# 3️⃣ Begin Knowledge Base Categories

Outcome: Organized sections created

We are not filling content yet.
We are creating a scalable library.

Think: future-proof.

## 🔹 Top-Level Categories

Create major buckets:

- Client Journey

- Sales & Consult Process

- Dispute Process

- Report Access (1B / 3B)

- Automations & Zaps

- Compliance & Legal

- Objection Handling

- Internal SOPs

- Tech Troubleshooting

- Refund Prevention & Retention

## 🔹 Inside Each Category, Add Subfolders

Example:

### Report Access

- 1B Access Process

- Security Question Process

- Login Retrieval

- Upgrade to 3B

- Report Sync Issues

Keep titles outcome-based, not vague.

Bad: “Credit stuff”
 Good: “Client Cannot Access IdentityIQ – Resolution Flow”

# 4️⃣ Create Placeholder for 1B → 3B Flow

Outcome: Framework ready for insertion

This needs to be built like a pipeline, not a paragraph.

## 🔹 Create a Visual Flow Structure

Step 1: Client signs up with 1B
 Step 2: Consultant builds dispute on 1B
 Step 3: Upgrade offer presented
 Step 4: Client pays upgrade
 Step 5: Remove 1B report
 Step 6: Upload 3B via one-click report uploader
 Step 7: Dispute form auto-updates
 Step 8: QA verification
 Step 9: Client confirmation

## 🔹 Include 3 Sections in This Placeholder

- When upgrade is offered

- When upgrade is mandatory

- What breaks if done incorrectly

Add a section labeled:
 “Common Failure Points”

Examples:

- Consultant forgets to remove 1B before upload

- Dispute form duplicates

- Client upgrades but no update done

- Zap fails

# Strategic Intention Behind Phase 1

We are:

- Removing dependency on memory

- Reducing Slack questions

- Eliminating gray areas

- Making onboarding easier

- Making audits easier

- Making scale possible

This structure should allow:

- A new hire to find answers without asking

- A manager to audit without digging

- Leadership to see gaps instantly

# Scripts for Joe to review

# 📞 SCRIPT 1: Setting Expectations – 1 Bureau Consultation

Consultant:
 “Before we get started, I want to set expectations so there’s no confusion. Today’s consultation is based on one credit bureau. There are actually three major bureaus — Equifax, Experian, and TransUnion — and each can report different accounts.

What this means:

- We may not see every negative account today.

- Some accounts could appear on the other two bureaus.

- Scores can differ between bureaus.

Our goal is to give you a clear picture of this report and explain how we can start improving your credit. Once we pull all three bureaus, we’ll be able to address everything completely.”

(Pause for acknowledgment)

If they ask why only one bureau:
 “Great question. Creditors don’t always report to all three bureaus, which is why we review each separately. Pulling all three later ensures nothing gets missed.”

# 💳 SCRIPT 2: Closing After $149 Payment – Explaining 3 Bureau Reports

Consultant:
 “Awesome! I’m excited to get started on improving your credit.

Next step: in order to officially launch your credit repair process and maximize results, we need all three bureau reports. Right now we only reviewed one. If we don’t access all three, any negative accounts on the others will still be visible and continue affecting your score.

By activating all three bureaus — Equifax, Experian, and TransUnion — we can:

- Identify all negative accounts

- File accurate disputes

- Track score improvements

- Prevent surprises from unseen accounts

This step ensures your investment delivers full results, not just partial improvements. Once we have all three, your process officially begins.”

# 🚫 SCRIPT 3: If Client Refuses $29.99 for IdentityIQ

Consultant:
 “I understand wanting to avoid extra costs. Let me explain why this step is necessary.

The $29.99 is for IdentityIQ, which gives us access to all three bureaus. This isn’t a fee for us — it’s what allows us to see everything so we can do disputes correctly. Here's why we recommend Identity IQ over any other provider. Most Providers like Experian.com only give you 50-60% of your actual credit report data and it's not that they don’t want to show you all your data, its that most credit report data is like a mile long and it's nearly impossible to push all that data onto a credit report. Identity IQ instead gives us 100% of your full credit report data which allows us to sometimes see discrepancies and inaccuracies before we already start disputing which helps our overall success rate.

If your goal is real, full credit improvement, this step is required. Think of it as protecting your investment.

(Pause for acknowledgment)

If they push back, try:

- Outcome-focused: “Without this, we can’t officially start the process. We want to give you the best results possible.”

- Cost perspective: “$29.99 gives you full visibility across all three bureaus — less than a dollar a day to protect your credit.”

- Direct, professional: “I want to be honest — we can’t deliver complete results without 3-bureau access.”

✅ Key Consultant Mindset:

- You’re protecting their results, not selling a product.

- Emphasize full improvement, accuracy, and investment protection.

- Keep it conversational and confident — objections are normal, not a sign of failure.

# 🚨 SCRIPT: If Client Says “I Want Other Options / You Weren’t Upfront”

Consultant:
 “I understand, and I appreciate you being upfront — that makes sense. Here’s why we do it this way:

Most of our clients who don’t get their FREE Credit Blueprint have to pull their credit reports before we can even do a consultation. In your case, we already had access to one of your bureaus, so we were able to do a full consultation without you having to pull all three upfront.

The great news is we were able to show you what we can do and how we can help before you went through the normal process. Now that you’ve decided to move forward, we want to make sure we’re disputing across all three bureaus, not just one, so nothing gets missed.

You have two options:

- Full 3-bureau process (recommended): We see everything and can fully improve your credit.

- Partial review: We only work with this bureau, so some negative accounts will still affect your score and results will be limited.

Our goal is to make sure your investment actually improves your credit. You decide which option works best for you.”

# McCarthy Law App Process

✅ McCarthy Law (MCL) App — Team Process & SOP

Part 1: Understanding McCarthy Law & the goal

## 🧑‍⚖️ What McCarthy Law Does

McCarthy Law is a law firm that looks closely at our clients’ credit reports to find mistakes.

### Examples of mistakes they look for:

- An account shows “settled” on one credit bureau but still shows a balance on another

- The same account appears twice (duplicate)

- Information that is wrong or incomplete

👉 If they find a serious mistake that breaks the law, they may take legal action for the client.

👉 In some cases, the client could receive up to $2,500 in compensation.

## 📜 What FCRA Means

FCRA stands for the Fair Credit Reporting Act.

It is a U.S. law that makes sure credit reports are:

- Accurate

- Fair

- Private

## ✅ What the FCRA Requires

The law says credit bureaus and creditors must:

- Report information correctly and completely

- Investigate disputes on time

- Fix or remove information they can’t verify

- Limit who can see your credit report

- Let consumers get a copy of their credit reports

## 🚩 Why This Matters in Credit Repair

An FCRA violation can happen when:

- Balances don’t match across credit bureaus

- A creditor does not properly investigate a dispute

- Duplicate accounts appear

- Old or wrong information keeps reporting when it shouldn’t

👉 When a real violation is proven, the client may have the right to:

- Get the item corrected or removed

- Possibly receive financial compensation up to $2,500

## 🎯 Why ASAP Credit Repair Offers This

ASAP Credit Repair offers this service to help clients get the best possible results.

### Our goals:

- Fix problems that normal disputes may not resolve

- Give clients extra protection when errors are serious

- Build trust by offering more complete help

- Support clients with legal review when needed

- Stand out from companies that only do basic disputes

## Part 2: App Pipelines & What to do

Below, we will explain why this is important, go over the daily steps, and show the different stages of the app and how to work through each one.

### 🎯 Purpose of this APP

This process helps the team make sure we:

- Keep track of MCL-eligible clients

- Finish follow-ups on time

- Move clients through the correct stages

- Keep all data clean and accurate

### 🔄 Daily Startup Process

Step 1: Log In

- Open and log into the MCL app.

Step 2: Sync Sheet (REQUIRED)

- Click Sync Sheet every time you log in

- Wait until the sync is finished

- Make sure the data has refreshed

### 📞 First Attempt – Need to Call

What it means:

- The client has not been reached yet and needs a call

When a client goes here:

- They are a newly added lead

- Follow-up is needed

What to do:

- Call the client

- If no answer → send text or email

- Document your attempt

- Move the client’s status once they respond

✅ Goal: Make the first successful contact

### 🚫 Do Not Call

What it means:

- The client should not be contacted by phone/email/text

When to use it:

- The client cannot be helped

- There is a compliance or legal restriction

What to do:

- Add a note explaining why

- Do NOT continue trying to contact

⚠️ Important:

- Do not use this just because the client is hard to reach

## 📲 LVM (Left Voicemail)

Meaning:
 A voicemail has been left and you are awaiting response.

When to move here:

- You called

- No answer

- Voicemail successfully left

Team actions:

- Send follow-up text/email

- Schedule next follow-up

- Monitor for response

✅ Goal: Get client to respond

## 💬 Contacted

Meaning:
 You have successfully spoken with the client.

Use when:

- Live conversation occurred

- Client engaged via phone/text/email

- Initial discussion completed

Next step depends on outcome:

- Interested → move forward

- Needs time → follow-up scheduled

- Not interested → move to Lost

## ⏳ Waiting on MCL

Meaning:
 The client has responded “YES” to the email

Client is:

- Will wait for McCarthy to reach out

- Reviewing info

- Not yet mailed packet

Team actions:

- Set follow-up reminder

- Continue nurture

- Answer questions

✅ Goal: Move client to Packet Sent

## 📦 Packet Sent (This will be edit by McCarthy)

Meaning:
 Client has been sent the MCL packet/envelope.

When to use:

- Packet mailed

- Client confirmed receipt (if applicable)

Team actions:

- Follow up to confirm mailing

- Monitor for return

- Provide support if needed

## 📬 Disputes Mailed  (This will be edit by McCarthy)

Meaning:
 Client has mailed the dispute/envelope.

Use when:

- Client confirms envelope mailed

- Tracking confirms shipment (if available)

Team actions:

- Update notes

- Move toward reports stage

- Monitor timeline

## 📊 Waiting on Reports

Meaning:
 Disputes are in process and we are waiting for credit bureau results.

Client is:

- In the waiting period

- No action needed from client

Team actions:

- Calendar follow-up

- Monitor timeline

- Provide updates if client asks

## ⚖️ Litigation ($500)

Meaning:
 Client has qualified for or entered litigation phase.

⚠️ Use carefully

Only move here when:

- Confirmed litigation eligibility

- Directed by leadership

- Client paid litigation fee (if required)

Team actions:

- Ensure documentation complete

- Follow legal workflow

- Minimal outbound unless required

## ❌ Lost

Meaning:
 The client is no longer moving forward.

Use when client:

- Declines service

- Stops responding after full follow-up cycle

- Working with another company

- Not qualified

Before marking Lost:
 ✅ Complete required attempts
 ✅ Add detailed note

# 🔄 REQUIRED DAILY WORKFLOW

Every agent must:

- Sync sheet at login

- Work Need to Call list

- Document every attempt

- Move clients immediately after status change

- Keep notes clean and specific

## Part 2: App Pipelines & What to do